## TQF-P78-KES-DD-HUL-SUB-0001
| PROJECT: | PETROBRAS 78 (P-78) | Date: | 28/12/2021 | Query n.º: | TQF-P78-KES-DD-HUL-SUB-00XX | [[[[[[[Select]]]]]]
| Discipline: | SUB |  |  | Query Rev.: | 0 | Missing Pages | Released
| From: | KEPPEL Shipyard Ltd |  |  | To: | PETROBRAS | Illegible Pages | Comments Added
| Issued by: | Kyungrock Son |  |  | Replied by: |  | Omissions | Not Released
| Checked by: | Youngchul Choi |  |  | Checked by: |  | Errors
| Released by: | Choong Kim Whye |  |  | Released by: |  | Inconsistencies
| Subject: | Hull Dismountable Sheave Location at 31S/45S/46S Slots
| Query Type: | Others |  |  | Reply Status:
REFERENCE DOCUMENTS: | I-DE-3A36.06-1500-941-P56-001_E Riser Supports Arrangement Conceptual Design FPSO Balcony I-RL-3A36.06-1500-274-PLR-001_0 Risers Interface - Preliminary Deviation Sheaves Positioning P-78
TAGs | Z-5139509A, Z-5139509B, Z-5139509C, Z-5139509D, Z-5139509E
ATTACHMENTS:
QUERY DETAILS: |  |  | REPLY DETAILS
This TQF is raised to request Buyer's confirmation regarding location of hull dismountable sheaves at slot number 31S/45S/46s, receptacles. Seller arranged hull dismountable sheaves for slot number 31S/45S/46S as attachment #1. Seller was confirmed regarding hull dismountable sheave location for 45S and 46S slots by Buyer via meeting on 28-Dec-21. In case of 31S slot, Seller would like to keep the current sheaves location which was arranged by Seller, as much as possible. Also, Seller would like to request Buyer's advice for hull dismountable sheaves location, if any change is required. Buyer's kind confirmation and advice would be appreciated. |  |  | REPLY DETAILS BY PETROBRAS
This TQF reply is only a technical clarification. Contractor shall not use this document as a scope change request. Any change of scope, cost and schedule, shall follow the procedures set in the contract.
Status by Petrobras
<#1>